## Sheet1
Topic | CIG | VG | CSG | CG
Business requirements breakdown - SO | intitated | finalized
Business requirements breakdown - BR,StR | intitated | detailed
Business requirements breakdown - SoR, TR |  |  | intitated
Business requirements breakdown - ATR |  |  | intitated
As-Is architectural drawbacks and limitations |  | intitated
Software change and configuration management plan |  | intitated
Total project time plan, Project approach |  | Detailed
EA start-up meeting performed |  | finalized
Impacted information flows* |  |  | intitated
Integration request - business part* |  |  | intitated
Business requirements prototype(s)* |  |  | intitated
Business requirements prototype(s): Business rules/scenarios |  |  | intitated
Business requirements prototype(s): Analysis artifacts |  |  | intitated
Software change and configuration management plan |  |  | detailed
Solution alternatives |  |  | finalized